## Sheet1
GROUP 5
Deep M. Prajapati
Vishal Patel
Urvesh Patel
Akshat Talajiya
Deep P. Prajapati
Date | Name | Task
11/05/2023 | Deep M. Prajapati | Discussed the project sitemap and researched the features
11/05/2023 | Vishal Patel | Discussed the project sitemap and researched the features
11/05/2023 | Urvesh Patel | Discussed the project sitemap and researched the features
11/05/2023 | Akshat Talajiya | Discussed the project sitemap and researched the features
11/05/2023 | Deep P. Prajapati | Discussed the project sitemap and researched the features
11/08/2023 | Vishal Patel | Created the website logo
11/10/2023 | Deep M. Prajapati | Drew the wireframe for service page
11/10/2023 | Deep P. Prajapati | Drew the wireframe for About Us page
11/12/2023 | Akshat Talajiya | Drew the wireframe for contact us page
11/14/2023 | Urvesh Patel | Drew the sitemap for the website
11/16/2023 | Urvesh Patel | Made header and footer for all pages
11/16/2023 | Vishal Patel | worked on index page
11/16/2023 | Deep M. Prajapati | coded the service page
11/16/2023 | Deep P. Prajapati | completed the html coding for About us page
11/17/2023 | Akshat Talajiya | started workiing on Contact page
11/17/2023 | Deep M. Prajapati | created Css for Service page
11/18/2023 | Vishal Patel | worked on index page css
11/18/2023 | Akshat Talajiya | completed coding of the about page and started working on css
11/19/2023 | Deep P. Prajapati | worked on Css for About us page (made it desktop responsive)
11/20/2023 | Urvesh Patel | working on package page
11/21/2023 | Deep P. Prajapati | completed css for About us page(made it tablet responsive)
11/21/2023 | Vishal Patel | added more content on index page
11/21/2023 | Akshat Talajiya | completed css for contact us page (design)
11/21/2023 | Urvesh Patel | worked more on package page
11/22/2023 | Vishal Patel | completed the tablet responsive for home page
11/22/2023 | Urvesh Patel | created word file for the documentation.
11/22/2023 | Deep M. Prajapati | made Service page fully responsive for all the devices.
11/22/2023 | Deep P. Prajapati | worked on home page along with Vishal and helped to make some css changes
11/23/2023 | Akshat Talajiya | made the contact page fully responsive
11/24/2023 | Deep M. Prajapati | completed package page and made it fully responsive
11/25/2023 | Deep M. Prajapati | created Package detail page
11/25/2023 | Deep P. Prajapati | created css for package detail page
11/26/2023 | Urvesh Patel | started creating Booking detail page
11/26/2023 | Deep M. Prajapati | worked on Booking detail page
11/28/2023 | Deep M. Prajapati | completed Booking detail page (both html and css)
11/29/2023 | Vishal Patel | made some changed to the home page (for mobile view)
11/29/2023 | Akshat Talajiya | made some changed to the contact us page (for mobile view)
11/30/2023 | everyone (worked in college) | reviewed the whole website and made few changes where required.
12/02/2023 | everyone (worked in college) | finalized the whole project and completed the documentation